Project Planning Phase

# Project Planning Report

Project: Script-Controlled ACL – Restrict Record Access Based on Field Value

| Date | 1 October 2026 |
| --- | --- |
| Team ID | SWTID-2026-7653 |
| Project Name | Script-Controlled ACL – Restrict Record Access Based on Field Value |
| Maximum Marks | 5 Marks |

# 1. Planning approach

This plan converts the Script-Controlled ACL lab into an Agile delivery plan. The work is organized as epics, user stories and three short sprints. Story points use the Fibonacci-style scale referenced by the Phase 4 planning logic: 1, 2, 3 and 5, where larger values represent greater uncertainty or effort.

Figure 1. Custom project-specific sprint roadmap; template sample imagery was not reused.

# 2. Planning terminology applied

| Term | Application in this project |
| --- | --- |
| Epic | A major capability group: foundation, ACL build, or validation/hardening. |
| User story | A small, testable implementation task written from the perspective of a user or administrator. |
| Story point | Relative effort estimate considering configuration, scripting, testing and uncertainty. |
| Sprint | A fixed five-working-day delivery period with a demonstrable increment. |
| Velocity | Average story points completed per sprint; used for capacity planning, not as a quality measure. |

# 3. Product backlog

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data foundation | USN-1 | As an administrator, I can create `u_institution_details` with the required table settings. | 3 | High | Project team |
| Sprint-1 | Data foundation | USN-2 | As an administrator, I can add the roll number, references, Branch, contact and Description fields. | 2 | High | Project team |
| Sprint-1 | Identity and roles | USN-3 | As a security administrator, I can create the EEE test user for controlled verification. | 2 | High | Security admin |
| Sprint-1 | Identity and roles | USN-4 | As a security administrator, I can create `bb1`–`bb4` and assign the intended role ladder. | 2 | High | Security admin |
| Sprint-2 | ACL implementation | USN-5 | As a branch user, I can read only EEE records when I have `bb1`; administrators retain full access. | 5 | High | ACL developer |
| Sprint-2 | ACL implementation | USN-6 | As an authorized user, I can create records when I have `bb2`. | 2 | High | ACL developer |
| Sprint-2 | ACL implementation | USN-7 | As an authorized user, I can write records when I have `bb3`. | 2 | High | ACL developer |
| Sprint-2 | ACL implementation | USN-8 | As an authorized user, I can delete records when I have `bb4`. | 2 | Medium | ACL developer |
| Sprint-3 | Validation and hardening | USN-9 | As a tester, I can impersonate representative users and verify each CRUD outcome. | 3 | High | QA / team |
| Sprint-3 | Validation and hardening | USN-10 | As a project reviewer, I can inspect evidence screenshots and a completed permission matrix. | 2 | Medium | Documentation |
| Sprint-3 | Validation and hardening | USN-11 | As a security administrator, I can test negative cases and document production hardening actions. | 3 | High | Security admin |

# 4. Sprint schedule and release plan

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (planned) | Sprint Release Date (planned) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 5 working days | 05 Oct 2026 | 09 Oct 2026 | 9 | 09 Oct 2026 |
| Sprint-2 | 11 | 5 working days | 12 Oct 2026 | 16 Oct 2026 | 11 | 16 Oct 2026 |
| Sprint-3 | 8 | 5 working days | 19 Oct 2026 | 23 Oct 2026 | 8 | 23 Oct 2026 |

Release plan: each sprint produces a usable increment in the same ServiceNow development instance. Sprint 1 establishes the data and identity foundation; Sprint 2 adds the ACL policy layer; Sprint 3 verifies behavior, captures evidence and prepares the project for review.

# 5. Project tracker and definition of done

| Workstream | Tracker checkpoints | Definition of done |
| --- | --- | --- |
| Foundation | Table exists; fields match the data model; sample ECE/EEE/CSE records exist. | Configuration saved, records load correctly, and evidence is captured. |
| ACL implementation | Each operation has an active ACL, correct role and documented behavior. | READ/CREATE/WRITE/DELETE outcomes are reproducible through impersonation. |
| Validation | Positive and negative cases executed; admin bypass verified. | Test results and screenshots are mapped to acceptance criteria. |
| Documentation | Permission matrix, limitations and hardening actions recorded. | Reviewer can understand how access is granted or denied without opening the instance. |

# 6. Velocity calculation

| Sprint | Planned completed points | Capacity interpretation |
| --- | --- | --- |
| Sprint-1 | 9 | Foundation and role setup |
| Sprint-2 | 11 | Highest-complexity ACL scripting and configuration |
| Sprint-3 | 8 | Verification, evidence and hardening |
| Total | 28 | Total estimated scope |

Average planned velocity = total planned story points ÷ number of sprints = 28 ÷ 3 = 9.33 story points per sprint. Because this is an initial plan with no historical team data, 9.33 is a planning baseline rather than a measured team velocity. After Sprint 1, the remaining sprint capacity should be recalibrated using completed work and any discovered ACL complexity.

# 7. Planned burndown chart

Figure 2. Planned burndown for the 28-point backlog; the forecast should be replaced with actual sprint-review data.

# 8. Project evidence and planning traceability

The plan is grounded in the existing project implementation rather than a generic software example. The following evidence links backlog items to the work described in the source project document.

## USN-2: field configuration evidence

The source project shows the table-column configuration for the institution details table, supporting the data-foundation stories.

Project evidence screenshot: USN-2: field configuration evidence

## USN-5: READ ACL scripting evidence

The source project shows the branch data condition and advanced script used to evaluate the READ policy.

Project evidence screenshot: USN-5: READ ACL scripting evidence

## USN-5 to USN-8: ACL operation evidence

The source project shows an operation-specific ACL form with role and table configuration, supporting the CRUD implementation stories.

Project evidence screenshot: USN-5 to USN-8: ACL operation evidence

## USN-9: verification data context

The source project shows the institution records list with branch values used to verify access outcomes.

Project evidence screenshot: USN-9: verification data context

# 9. Risks, assumptions and planning controls

Assumption: the project team has access to a ServiceNow instance with permission to elevate `security_admin` when creating ACLs.

Risk: create/write/delete may require branch-specific conditions in a production policy even though the lab design explicitly applies the Branch condition to READ; resolve this in Sprint 3 hardening.

Risk: role inheritance or pre-existing ACLs may change observed results; test in a clean or documented instance and record baseline configuration.

Control: use impersonation-based acceptance tests for no-role, bb1, bb1+bb2, bb1+bb2+bb3, bb1+bb2+bb3+bb4 and admin states.

Control: treat the velocity as a forecast until actual completed points are available; do not add scope without re-estimating the burndown.

# 10. Conclusion

The Phase 4 plan delivers the ACL project in three manageable increments with a 28-point backlog, explicit ownership, planned release dates, a measurable velocity baseline and a burndown forecast. It preserves the project’s security objective while adding the planning artifacts needed to execute, review and improve the implementation.

# References

Primary source: project document “Script-Controlled ACL – Restrict Record Access Based on Field Value,” supplied by the project owner. Planning structure adapted from the supplied Phase 4 Project Planning Template and Planning logic document. Template references include Atlassian Agile/Scrum guidance and Visual Paradigm burndown-chart guidance.